Lower Florida Keys Hospital District

March 3, 2026

Board meeting

Akerman Report

- RFP Status

  - Akerman has folded in comments, changes, recommendations made at last Bd meeting, stakeholder input and additional Florida regulatory requirements

  - Akerman continues to work with Stroudwater to develop criteria, collect market data to reflect needs and criteria and other RFP sections as necessary

  - Developing timeline and procedures for RFP process, interviews, criteria, public input, negotiation and contract engagement

  - Analyzing engineer report, and will make recommendations for RFP not only to include as exhibit, but include section of RFP as needed to address facility matters.

  - Coordinate site visit for Prospect Bidders after Bid publication

  - Akerman will create landing page or we can use DemandStar or MyFloridaMarketPlace. TBD.  Also TBD are publications like newspaper, Florida Register, trade publications.

  - Stroudwater and Akerman are building RFP modifications, criteria (based on questions presented in the RFP) and gathering data to make adjustments to RFP

Criteria: Quality and Reputation ; Services Commitment; Workforce Commitment; System Integration; Investment commitment; Indigent Care commitment; Facility

- Stakeholder Input

  - Akerman continues to meet with stakeholders in the community, in the health care field and is soliciting information, market analysis, data, opinions

  - Welcome the opportunity to discuss the input of community members.

- RFP Process Following Receipt of Engineer Report

  - Following Engineer report, Akerman will then have about 30 days to provide the Board a redraft of the RFP with the engineer report aspects